AGREEMENT made as of the «20th» day of «October» in the year «2023»

(In words, indicate day, month and year.)

BETWEEN the Owner:

(Name, legal status, address, and other information)

Mississippi State University

P.O. Box 5307

Mississippi State, MS 39762-5307

and the Construction Manager:

(Name, legal status, address, and other information)

for the following Project:

(Name, location, and detailed description)

The Architect:

(Name, legal status, address, and other information)

The Owner and Construction Manager agree as follows.

TABLE OF ARTICLES

1	INITIAL INFORMATION

2	CONSTRUCTION MANAGER’S RESPONSIBILITIES

3	SCOPE OF CONSTRUCTION MANAGER’S BASIC SERVICES

4	SUPPLEMENTAL AND ADDITIONAL SERVICES

5	OWNER’S RESPONSIBILITIES

6	COST OF THE WORK

7	COPYRIGHTS AND LICENSES

8	CLAIMS AND DISPUTES

9	TERMINATION OR SUSPENSION

10	MISCELLANEOUS PROVISIONS

11	COMPENSATION

12	SPECIAL TERMS AND CONDITIONS

13	SCOPE OF THE AGREEMENT

# ARTICLE 1   INITIAL INFORMATION

§ 1.1 This Agreement is based on the Initial Information set forth in this Section 1.1.

(For each item in this section, insert the information or a statement such as “not applicable” or “unknown at time of execution.”)

§ 1.1.1 The Owner’s program for the Project:

(Insert the Owner’s program, identify documentation that establishes the Owner’s program, or state the manner in which the program will be developed.)

Project description

§ 1.1.2 The Project’s physical characteristics:

(Identify or describe pertinent information about the Project’s physical characteristics, such as size; location; dimensions; geotechnical reports; site boundaries; topographic surveys; traffic and utility studies; availability of public and private utilities and services; legal description of the site, etc.)

N/A

§ 1.1.3 The Owner’s budget for the Cost of the Work, as defined in Section 6.1:

(Provide total and, if known, a line item breakdown.)

TBD

§ 1.1.4 The Owner’s anticipated design and construction milestone dates:

.1	Design phase milestone dates, if any:

TBD

.2	Construction commencement date:

.3	Substantial Completion date or dates:

TBD

.4	Other milestone dates:

N/A

§ 1.1.5 The Owner intends the following procurement method for the Project:

(Identify method such as competitive bid or negotiated contract.)

Competitive Bid in accordance with applicable Mississippi Law

§ 1.1.6 The Owner’s requirements for accelerated or fast-track design and construction, multiple bid packages, or phased construction are set forth below:

(Identify any requirements for fast-track scheduling or phased construction and, if applicable, list number and type of bid/procurement packages.)

N/A

§ 1.1.7 The Owner’s anticipated Sustainable Objective for the Project:

(Identify and describe the Owner’s Sustainable Objective for the Project, if any.)

N/A

§ 1.1.7.1 If the Owner identifies a Sustainable Objective, the Owner and Construction Manager shall complete and incorporate AIA Document E235™–2019, Sustainable Projects Exhibit, Construction Manager as Adviser Edition, into this Agreement to define the terms, conditions and services related to the Owner’s Sustainable Objective. If E235–2019 is incorporated into this Agreement, the Owner and Construction Manager shall incorporate the completed E235–2019 into the agreements with the consultants and contractors performing services or Work in any way associated with the Sustainable Objective.

§ 1.1.8 Other Project information:

(Identify special characteristics or needs of the Project not provided elsewhere.)

N/A

§ 1.1.9 The Owner identifies the following representative in accordance with Section 5.5:

(List name, address, and other contact information.)

Ches Fedric, Director of Planning, Design & Construction Administration

Office of Planning, Design & Construction Administration

Gast Building, 130 Twelve Lane

Mississippi State, MS 39762

P: 662.325.8213

E: ecf17@msstate.edu

§ 1.1.10 The persons or entities, in addition to the Owner’s representative, who are required to review the Construction Manager’s submittals to the Owner are as follows:

(List name, address, and other contact information.)

architect

§ 1.1.11 The Owner shall retain the following consultants and Contractors:

(List name, legal status, address, and other contact information.)

.1	Land Surveyor:

N/A

.2	Geotechnical Engineer:

N/A

.3	Civil Engineer:

N/A

.4	Contractors, as defined in Section 1.4:

TBD

.5	Separate Contractors, as defined in Section 1.4:

TBD

.6	Other, if any:

(List any other consultants retained by the Owner.)

TBD

§ 1.1.12 The Construction Manager identifies the following representative in accordance with Section 2.5:

(List name, address, and other contact information.)

CMa

§ 1.1.13 The Construction Manager’s staffing plan as required under Section 3.3.3 shall include:

(List any specific requirements and personnel to be included in the staffing plan, if known.)

TBD

§ 1.1.14 The Construction Manager’s consultants retained under Basic Services, if any:

(List name, legal status, address, and other contact information of any consultants.)

TBD

§ 1.1.15 The Construction Manager’s consultants retained under Supplemental Services:

TBD

§ 1.1.16 Other Initial Information on which this Agreement is based:

None

§ 1.2 The Owner and Construction Manager may rely on the Initial Information. Both parties, however, recognize that the Initial Information may materially change and, in that event, the Owner and the Construction Manager shall appropriately adjust the Construction Manager’s services, schedule for the Construction Manager’s services, and the Construction Manager’s compensation. The Owner shall adjust the Owner’s budget for the Cost of the Work and the Owner’s anticipated design and construction milestones, as necessary, to accommodate material changes in the Initial Information.

§ 1.3 The parties shall agree upon protocols governing the transmission and use of Instruments of Service or any other information or documentation in digital form. The parties will use AIA Document E203™–2013, Building Information Modeling and Digital Data Exhibit, to establish the protocols for the development, use, transmission, and exchange of digital data.

§ 1.3.1 Any use of, or reliance on, all or a portion of a building information model without agreement to protocols governing the use of, and reliance on, the information contained in the model and without having those protocols set forth in AIA Document E203™–2013, Building Information Modeling and Digital Data Exhibit, and the requisite AIA Document G202™–2013, Project Building Information Modeling Protocol Form, shall be at the using or relying party’s sole risk and without liability to the other party and its contractors or consultants, the authors of, or contributors to, the building information model, and each of their agents and employees.

§ 1.4 The term “Contractors” refers to persons or entities who perform Work under contracts with the Owner that are administered by the Construction Manager and Architect. The term “Contractors” is used to refer to such persons or entities, whether singular or plural. The term does not include the Owner’s own forces, or Separate Contractors, which are persons or entities who perform construction under separate contracts with the Owner not administered by the Construction Manager and Architect.

# ARTICLE 2   CONSTRUCTION MANAGER’S RESPONSIBILITIES

§ 2.1 The Construction Manager shall provide the services as set forth in this Agreement.

§ 2.2 The Construction Manager shall perform its services consistent with the skill and care ordinarily provided by construction managers practicing in the same or similar locality under the same or similar circumstances. The Construction Manager shall perform its services as expeditiously as is consistent with such skill and care and the orderly progress of the Project.

§ 2.3 The Construction Manager shall provide its services in conjunction with the services of an Architect as described in AIA Document B132™–2019, Standard Form of Agreement Between Owner and Architect, Construction Manager as Adviser Edition. The Construction Manager shall not be responsible for actions taken by the Architect.

§ 2.4 The Construction Manager shall coordinate its services with those services provided by the Owner, the Architect, the Contractors, and the Owner’s other consultants and Separate Contractors. The Construction Manager shall be entitled to rely on, and shall not be responsible for, the accuracy and completeness of services and information furnished by the Owner, the Architect, and the Owner’s other consultants and Separate Contractors. The Construction Manager shall provide prompt written notice to the Owner if the Construction Manager becomes aware of any error, omission, or inconsistency in such services or information.

§ 2.5 The Construction Manager shall identify a representative authorized to act on behalf of the Construction Manager with respect to the Project.

§ 2.6 The Construction Manager, as soon as practicable after execution of the Agreement, shall notify the Owner in writing of the names and qualifications of its proposed key staff members. Within 14 days of receipt of the names and qualifications of the Construction Manager’s proposed key staff members, the Owner may reply to the Construction Manager in writing, stating (1) whether the Owner has reasonable objection to a proposed key staff member or (2) that the Owner requires additional time to review. Failure of the Owner to reply within the 14-day period shall constitute notice of no reasonable objection. The Construction Manager shall not staff any employees on the Project to whom the Owner has made reasonable and timely objection. The Construction Manager shall not change its key staff members without the Owner’s consent, which shall not be unreasonably withheld or delayed.

§ 2.7 Except with the Owner’s knowledge and consent, the Construction Manager shall not engage in any activity, or accept any employment, interest or contribution that would reasonably appear to compromise the Construction Manager’s judgment with respect to this Project.

§ 2.8 The Construction Manager shall maintain the following insurance until termination of this Agreement. If any of the requirements set forth below are in addition to the types and limits the Construction Manager normally maintains, the Owner shall pay the Construction Manager as set forth in section 11.7.

§ 2.8.1 Commercial General Liability with policy limits of not less than «  » ($ «  » ) for each occurrence and «  » ($ «  » ) in the aggregate for bodily injury and property damage.

§ 2.8.2 Automobile Liability covering vehicles owned, and non-owned vehicles used, by the Construction Manager with policy limits of not less than «  » ($ «  » ) per accident for bodily injury, death of any person, and property damage arising out of the ownership, maintenance and use of those motor vehicles, along with any other statutorily required automobile coverage.

§ 2.8.3 The Construction Manager may achieve the required limits and coverage for Commercial General Liability and Automobile Liability through a combination of primary and excess or umbrella liability insurance, provided such primary and excess or umbrella liability insurance policies result in the same or greater coverage as the coverages required under Sections 2.8.1 and 2.8.2, and in no event shall any excess or umbrella liability insurance provide narrower coverage than the primary policy. The excess policy shall not require the exhaustion of the underlying limits only through the actual payment by the underlying insurers.

§ 2.8.4 Workers’ Compensation at statutory limits and Employers Liability with policy limits not less than «  » ($ «  » ) each accident, «  » ($ «  » ) each employee, and «   » ($ «  » ) policy limit.

§ 2.8.5 Professional Liability covering negligent acts, errors and omissions in the performance of professional services with policy limits of not less than «  » ($ «  » ) per claim and «  » ($ «  » ) in the aggregate.

§ 2.8.6 Additional Insured Obligations. To the fullest extent permitted by law, the Construction Manager shall cause the primary and excess or umbrella polices for Commercial General Liability and Automobile Liability to include the Owner as an additional insured for claims caused in whole or in part by the Construction Manager’s negligent acts or omissions. The additional insured coverage shall be primary and non-contributory to any of the Owner’s insurance policies and shall apply to both ongoing and completed operations.

§ 2.8.7 The Construction Manager shall provide certificates of insurance to the Owner that evidence compliance with the requirements in this Section 2.8.

§ 2.9 The Construction Manager shall assist the Owner, Architect, and other Project participants in establishing building information modeling and digital data protocols for the Project using AIA Document E203™–2013, Building Information Modeling and Digital Data Exhibit, to establish the protocols for the development, use, transmission, and exchange of digital data.

§ 2.10 A centralized electronic document management system will be used on the Project, and the Construction Manager shall be designated the Responsible Project Participant in section 3.5 of E203-2013, responsible for managing and maintaining the centralized electronic document management system. The centralized electronic document management system shall include all items listed in Article 3 of E203, and the following:

(List any items to be included that are not listed in Article 3 of E203-2013.)

None

§ 2.11 The Construction Manager shall retain all Project related documents and information it receives, and the Owner and Architect shall have access to the documents and information. The Construction Manager shall transmit the documents and information to the Owner at final completion.

# ARTICLE 3   SCOPE OF CONSTRUCTION MANAGER’S BASIC SERVICES

§ 3.1 Definition

The Construction Manager’s Basic Services consist of those described in this Article 3, and include usual and customary Preconstruction and Construction Phase Services. Services not set forth in this Article 3 are Supplemental or Additional Services. The Owner, Construction Manager, and Contractors may agree, in consultation with the Architect, for the Construction Phase to commence prior to completion of the Preconstruction Phase, in which case, both phases will proceed concurrently.

§ 3.2 Preconstruction Phase

§ 3.2.1 The Construction Manager shall review the program furnished by the Owner and any evaluation of the Owner’s program provided by the Architect, to ascertain the requirements of the Project and shall arrive at a mutual understanding of such requirements with the Owner and Architect.

§ 3.2.2 The Construction Manager shall provide a preliminary evaluation of the Owner’s program, schedule and construction budget requirements, each in terms of the other.

§ 3.2.3 The Construction Manager shall prepare, and deliver to the Owner, for the Owner’s approval, a written Construction Management Plan that includes, at a minimum, the following: (1) preliminary evaluations required in Section 3.2.2, (2) a Project schedule, (3) cost estimates, (4) recommendations for Project delivery method, and (5) Contractors’ scopes of Work. The Construction Manager shall periodically update the Construction Management Plan, for the Owner’s approval, over the course of the Project.

§ 3.2.4 The Construction Manager shall prepare and periodically update the Project schedule included in the Construction Management Plan for the Architect’s review and the Owner’s acceptance. The Construction Manager shall obtain the Architect’s approval for the portion of the Project schedule relating to the performance of the Architect’s services. The Project schedule shall coordinate and integrate the Construction Manager’s services, the Architect’s services, other Owner consultants’ services, and the Owner’s responsibilities and highlight items that affect the Project’s timely completion.

§ 3.2.5 The Construction Manager shall update the Project schedule to include the components of the Work, including phasing of construction, times of commencement and completion required of each Contractor, ordering and delivery of products, including those that must be ordered in advance of construction, obtaining the required reviews and approvals of authorities having jurisdiction over the Project, and the occupancy requirements of the Owner.

§ 3.2.6 Based on the preliminary design and information prepared or provided by the Architect and other Owner consultants, the Construction Manager shall prepare, for the Architect’s review and Owner’s approval, preliminary estimates of the Cost of the Work or the cost of program requirements using area, volume or similar conceptual estimating techniques, including the establishment of sufficient contingency to reasonably anticipate the development of the Project’s design documents.

§ 3.2.7 The Construction Manager shall review design documents during their development and advise the Owner and Architect on proposed site use and improvements, selection of materials, building systems, and equipment. The Construction Manager shall also provide recommendations to the Owner and Architect, consistent with the Project requirements, on constructability; availability of materials and labor; sequencing for phased construction; time requirements for procurement, installation and construction; and factors related to construction cost including, but not limited to, costs of alternative designs or materials, preliminary budgets, life-cycle data, and possible cost reductions.

§ 3.2.8 The Construction Manager shall review recommendations for systems, materials, or equipment for the impact upon cost, schedule, sequencing, constructability, and coordination among the Contractors. The Construction Manager shall discuss its findings with the Owner and the Architect, and coordinate resolution, as necessary, of any such impacts.

§ 3.2.9 As the Architect progresses with the preparation of the Schematic Design, Design Development and Construction Documents, the Construction Manager shall prepare and update, at appropriate intervals agreed to by the Owner, Construction Manager and Architect, an estimate of the Cost of the Work with increasing detail and refinement. The Construction Manager shall include in the estimate those costs to allow for further development of the design, bidding or negotiating, price escalation, and market conditions. The estimate shall be provided for the Architect’s review and the Owner’s approval. The Construction Manager shall inform the Owner and Architect in the event that the estimate of Cost of the Work exceeds the latest approved Project budget, and make recommendations for corrective action.

§ 3.2.10 As the Architect progresses with the preparation of the Schematic Design, Design Development and Construction Documents, the Construction Manager shall consult with the Owner and Architect and make recommendations whenever the Construction Manager determines that the design, or details, adversely affect cost, scope, schedule, constructability, or quality of the Project.

§ 3.2.11 The Construction Manager shall provide recommendations and information to the Owner and Architect regarding the assignment of responsibilities for temporary Project facilities and equipment, materials and services for common use of the Contractors. The Construction Manager shall verify that such requirements and assignment of responsibilities are included in the proposed Contract Documents.

§ 3.2.12 The Construction Manager shall provide recommendations and information to the Owner regarding the allocation of responsibilities for safety programs among the Contractors.

§ 3.2.13 The Construction Manager shall provide recommendations to the Owner on the division of the Project into individual contracts for the construction of various categories of Work, including the method to be used for selecting Contractors and awarding Contracts for Construction. The Construction Manager shall review the Drawings and Specifications and make recommendations as required to provide that (1) the Work of the Contractors is coordinated, (2) all requirements for the Project are assigned to the appropriate Contract, (3) the likelihood of jurisdictional disputes is minimized, and (4) proper coordination is provided for phased construction.

§ 3.2.14 The Construction Manager shall make recommendations about, and coordinate the ordering and delivery of, materials in support of the schedule, including those that must be ordered in advance of construction.

§ 3.2.15 The Construction Manager shall assist the Owner in selecting, retaining, and coordinating the professional services of surveyors, geotechnical engineers, special consultants, and construction materials testing required for the Project.

§ 3.2.16 The Construction Manager shall provide an analysis of the types and quantities of labor required for the Project and review the availability of appropriate categories of labor required for critical phases. The Construction Manager shall make recommendations for actions designed to minimize adverse effects of labor shortages.

§ 3.2.17 The Construction Manager shall assist the Owner in obtaining information regarding applicable requirements for equal employment opportunity programs, and other programs as may be required by governmental and quasi- governmental authorities for inclusion in the Contract Documents.

§ 3.2.18 Following the Owner’s approval of the Drawings and Specifications, the Construction Manager shall update and submit the latest estimate of the Cost of the Work and the Project schedule for the Architect’s review and the Owner’s approval.

§ 3.2.19 The Construction Manager, in consultation with the Owner, shall develop bidders’ interest in the Project and establish bidding schedules. The Construction Manager shall assist the Owner and the Architect with the development of the Bidding Documents, which consist of bidding requirements and proposed Contract Documents. The Construction Manager, with the assistance of the Architect, shall issue Bidding Documents to bidders and conduct pre-bid conferences with prospective bidders. The Construction Manager shall issue the current Project schedule with each set of Bidding Documents. The Construction Manager shall assist the Architect with regard to questions from bidders and with the issuance of addenda.

§ 3.2.20 The Construction Manager shall submit a list of prospective bidders for the Architect’s review and the Owner’s approval.

§ 3.2.21 The Construction Manager, with the assistance of the Architect, shall review bids, and prepare bid analyses, and make recommendations to the Owner for the Owner’s award of Contracts for Construction or rejection of bids.

§ 3.2.22 The Construction Manager, with the assistance of the Architect, shall assist the Owner in preparing Contracts for Construction. The Construction Manager shall advise the Owner on the acceptability of Subcontractors and material suppliers proposed by Contractors.

§ 3.2.23 The Construction Manager shall assist the Owner in obtaining building permits and special permits for permanent improvements, except for permits required to be obtained directly by the Contractors. The Construction Manager shall verify that the Owner has paid applicable fees and assessments. The Construction Manager shall assist the Owner and Architect in connection with the Owner’s responsibility for filing documents required for the approvals of governmental authorities having jurisdiction over the Project.

§ 3.2.24 If the Owner identified a Sustainable Objective in Article 1, the Construction Manager shall fulfill its Preconstruction Phase responsibilities as required in AIA Document E235™–2019, Sustainable Projects Exhibit, Construction Manager as Adviser Edition, attached to this Agreement.

§ 3.3 Construction Phase

§ 3.3.1 The Construction Manager shall provide on-site administration of the Contracts for Construction in cooperation with the Architect as set forth below and in AIA Document A232™–2019, General Conditions of the Contract for Construction, Construction Manager as Adviser Edition. If the Owner and Contractor modify AIA Document A232–2019, those modifications shall not affect the Construction Manager’s services under this Agreement unless the Owner and the Construction Manager amend this Agreement.

§ 3.3.2 Subject to Section 4.2 and except as provided in Section 3.3.30, the Construction Manager’s responsibility to provide Construction Phase Services commences with the award of the initial Contract for Construction and terminates on the date the Architect issues the final Certificate for Payment.

§ 3.3.3 The Construction Manager shall provide a staffing plan to include one or more representatives who shall be in attendance at the Project site whenever the Work is being performed.

§ 3.3.4 The Construction Manager shall provide administrative, management and related services to coordinate scheduled activities and responsibilities of the Contractors with each other and with those of the Construction Manager, the Owner and the Architect. The Construction Manager shall coordinate the activities of the Contractors in accordance with the latest approved Project schedule and the Contract Documents.

§ 3.3.5 The Construction Manager shall review and analyze the construction schedules provided by the Contractors to update the Project schedule, incorporating the activities of the Owner, Architect, and Contractors on the Project, including activity sequences and durations, allocation of labor and materials, processing of Shop Drawings, Product Data and Samples, and delivery and procurement of products, including those that must be ordered in advance of construction. The Project schedule shall include the Owner’s occupancy requirements showing portions of the Project having occupancy priority. The Construction Manager shall update and reissue the Project schedule as required to show current conditions. If an update indicates that the previously approved Project schedule may not be met, the Construction Manager shall recommend corrective action to the Owner and Architect.

§ 3.3.6 The Construction Manager shall schedule and conduct meetings to discuss matters such as procedures, progress, coordination, and scheduling of the Work, and to develop solutions to issues identified. The Construction Manager shall prepare and promptly distribute minutes to the Owner, Architect and Contractors.

§ 3.3.7 In accordance with the Contract Documents and the latest approved Project schedule, and utilizing information from the Contractors, the Construction Manager shall review, analyze, schedule and coordinate the overall sequence of construction and assignment of space in areas where the Contractors are performing Work.

§ 3.3.8 The Construction Manager shall coordinate all tests and inspections required by the Contract Documents or governmental authorities, observe the on-site testing and inspections, and arrange for the delivery of test and inspection reports to the Owner and Architect.

§ 3.3.9 The Construction Manager shall endeavor to obtain satisfactory performance from each of the Contractors. The Construction Manager shall recommend courses of action to the Owner when requirements of a Contract are not being fulfilled.

§ 3.3.10 The Construction Manager shall monitor and evaluate actual costs for activities in progress and estimates for uncompleted tasks and advise the Owner and Architect as to variances between actual costs and budgeted or estimated costs. If a Contractor is required to submit a Control Estimate, the Construction Manager shall meet with the Owner and Contractor to review the Control Estimate. The Construction Manager shall promptly notify the Contractor if there are any inconsistencies or inaccuracies in the information presented. The Construction Manager shall also report the Contractor’s cost control information to the Owner.

§ 3.3.11 The Construction Manager shall develop cash flow reports and forecasts for the Project and include them in the Construction Manager’s progress reports.

§ 3.3.12 The Construction Manager shall maintain accounting records on authorized Work performed under unit costs, additional Work performed on the basis of actual costs of labor and materials, and other Work requiring accounting records.

§ 3.3.12.1 The Construction Manager shall develop and implement procedures for the review and processing of Applications for Payment by Contractors for progress and final payments.

§ 3.3.12.2 Not more frequently than monthly, the Construction Manager shall review and certify the amounts due the respective Contractors as follows:

.1	Where there is only one Contractor responsible for performing the Work, the Construction Manager shall, within seven days after the Construction Manager receives the Contractor’s Application for Payment, review the Application, certify the amount the Construction Manager determines is due the Contractor, and forward the Contractor’s Application and Certificate for Payment to the Architect.

.2	Where there is more than one Contractor responsible for performing different portions of the Project, the Construction Manager shall, within seven days after the Construction Manager receives each Contractor’s Application for Payment: (1) review the Applications and certify the amount the Construction Manager determines is due each Contractor; (2) prepare a Summary of Contractors’ Applications for Payment by summarizing information from each Contractor’s Application for Payment; (3) prepare a Project Application and Certificate for Payment; (4) certify the total amount the Construction Manager determines is due all Contractors collectively; and (5) forward the Summary of Contractors’ Applications for Payment and Project Application and Certificate for Payment to the Architect.

§ 3.3.12.3 The Construction Manager’s certification for payment shall constitute a representation to the Owner, based on the Construction Manager’s evaluations of the Work and on the data comprising the Contractors’ Applications for Payment, that, to the best of the Construction Manager’s knowledge, information and belief, the Work has progressed to the point indicated, the quality of the Work is in accordance with the Contract Documents, and the Contractors are entitled to payment in the amount certified. The foregoing representations are subject to (1) an evaluation of the Work for conformance with the Contract Documents upon Substantial Completion; (2) results of subsequent tests and inspections; (3) correction of minor deviations from the Contract Documents prior to completion; and (4) specific qualifications expressed by the Construction Manager. The issuance of a Certificate for Payment shall further constitute a recommendation to the Architect and Owner that the Contractor be paid the amount certified.

§ 3.3.12.4 The certification of an Application for Payment or a Project Application for Payment by the Construction Manager shall not be a representation that the Construction Manager has (1) made exhaustive or continuous on-site inspections to check the quality or quantity of the Work; (2) reviewed construction means, methods, techniques, procedures, or sequences for a Contractor’s own Work; (3) reviewed copies of requisitions received from Subcontractors and suppliers and other data requested by the Owner to substantiate each Contractor’s right to payment; or (4) ascertained how or for what purpose that Contractor has used money previously paid on account of the Contract Sum.

§ 3.3.13 The Construction Manager shall obtain and review the safety programs developed by each Contractor solely and exclusively for purposes of coordinating the safety programs with those of the other Contractors and for making recommendations for any additional safety measures to be considered in the Work of the Contractors. The Construction Manager’s responsibilities for coordination of safety programs shall not extend to direct control over or charge of the acts or omissions of the Contractors, Subcontractors, agents or employees of the Contractors or Subcontractors, or any other persons performing portions of the Work and not directly employed by the Construction Manager.

§ 3.3.14 The Construction Manager shall determine in general that the Work of each Contractor is being performed in accordance with the requirements of the Contract Documents and notify the Owner, Contractor and Architect of defects and deficiencies in the Work. The Construction Manager shall have the authority to reject Work that does not conform to the Contract Documents and shall notify the Architect about the rejection. The failure of the Construction Manager to reject Work shall not constitute acceptance of the Work. The Construction Manager shall record any rejection of Work in its daily log and include information regarding the rejected Work in its progress reports to the Architect and Owner pursuant to Section 3.3.22.1. Upon written authorization from the Owner, the Construction Manager may require and make arrangements for additional inspection or testing of the Work in accordance with the provisions of the Contract Documents, whether or not the Work is fabricated, installed or completed, and the Construction Manager shall give timely notice to the Architect of when and where the tests and inspections are to be made so that the Architect may be present for such procedures.

§ 3.3.15 The Construction Manager shall advise and consult with the Owner and Architect during the performance of its Construction Phase Services. The Construction Manager shall have authority to act on behalf of the Owner only to the extent provided in this Agreement. The Construction Manager shall not have control over, charge of, or responsibility for the construction means, methods, techniques, sequences or procedures, or for safety precautions and programs in connection with the Work of each of the Contractors, since these are solely the Contractor’s rights and responsibilities under the Contract Documents. The Construction Manager shall not be responsible for a Contractor’s failure to perform the Work in accordance with the requirements of the Contract Documents. The Construction Manager shall be responsible for the Construction Manager’s negligent acts or omissions, but shall not have control over or charge of, and shall not be responsible for, acts or omissions of the Contractors, Subcontractors, or their agents or employees, or any other persons or entities performing portions of the Work.

§ 3.3.16 The Construction Manager shall transmit to the Architect requests for interpretations, and requests for information of the meaning and intent of the Drawings and Specifications, and provide its written recommendation. The Construction Manager shall assist in the resolution of questions that may arise.

§ 3.3.17 The Construction Manager shall review requests for changes, assist in negotiating Contractors’ proposals, submit recommendations to the Architect and Owner, and, if the proposed changes are accepted or required by the Owner, prepare Change Orders or Construction Change Directives that incorporate the Architect’s modifications to the Contract Documents.

§ 3.3.18 The Construction Manager shall assist the Initial Decision Maker in the review, evaluation and documentation of Claims, subject to Section 4.2.2.7.

§ 3.3.19 Utilizing the submittal schedules provided by each Contractor, the Construction Manager shall prepare, and revise as necessary, a Project submittal schedule incorporating information from the Owner, Owner’s consultants, Owner’s Separate Contractors and vendors, governmental agencies, and participants in the Project under the management of the Construction Manager. The Project submittal schedule and any revisions shall be submitted to the Architect for approval.

§ 3.3.20 The Construction Manager shall promptly review all Shop Drawings, Product Data, Samples, and other submittals from the Contractors for compliance with the submittal requirements of the Contract, coordinate submittals with information contained in related documents, and transmit to the Architect those that the Construction Manager recommends for approval. The Construction Manager’s actions shall be taken in accordance with the Project submittal schedule approved by the Architect, or in the absence of an approved Project submittal schedule, with such reasonable promptness as to cause no delay in the Work or in the activities of the Contractors, the Owner, or the Architect.

§ 3.3.20.1 If professional design services or certifications by a design professional related to systems, materials, or equipment are specifically required of the Contractors by the Contract Documents, the Construction Manager shall review those submittals for sequencing, constructability, and coordination impacts on the other Contractors. The Construction Manager shall discuss its findings with the Owner and the Architect, and coordinate resolution, as necessary, of any such impacts.

§ 3.3.21 The Construction Manager shall keep a daily log containing a record of weather, each Contractor’s Work on the site, number of workers, identification of equipment, Work accomplished, problems encountered, and other similar relevant data as the Owner may require.

§ 3.3.21.1 The Construction Manager shall collect, review for accuracy, and compile the Contractors’ daily logs; and include them in the Construction Manager’s reports prepared and submitted in accordance with section 3.3.21.2.

§ 3.3.21.2 The Construction Manager shall record the progress of the Project. On a monthly basis, or otherwise as agreed to by the Owner, the Construction Manager shall submit written progress reports to the Owner and Architect, showing percentages of completion and other information identified below:

.1	Work completed for the period;

.2	Project schedule status;

.3	Submittal schedule and status report, including a summary of remaining and outstanding submittals;

.4	Request for information, Change Order, and Construction Change Directive status reports;

.5	Tests and inspection reports;

.6	Status report of nonconforming and rejected Work;

.7	Daily logs;

.8	Summary of all Contractors’ Applications for Payment;

.9	Cumulative total of the Cost of the Work to date including the Construction Manager’s compensation and reimbursable expenses at the job site, if any;

.10	Cash-flow and forecast reports;

.11	Photographs to document the progress of the Project;

.12	Status reports on permits and approvals of authorities having jurisdiction; and

.13	Any other items the Owner may require:

§ 3.3.21.3 In addition, for Projects constructed on the basis of the Cost of the Work, the Construction Manager shall include the following additional information in its progress reports:

.1	Contractors’ work force reports;

.2	Equipment utilization report;

.3	Cost summary, comparing actual costs to updated cost estimates; and

.4	Any other items as the Owner may require:

§ 3.3.22 Utilizing the documents provided by the Contractors, the Construction Manager shall make available, at the Project site, the Contract Documents, including Change Orders, Construction Change Directives, and other Modifications, in good order and marked currently to indicate field changes and selections made during construction, and the approved Shop Drawings, Product Data, Samples, and similar required submittals. These shall be in electronic form or paper copy, available to the Owner, Architect, and Contractors. Upon completion of the Project, the Construction Manager shall deliver them to the Owner.

§ 3.3.23 The Construction Manager shall arrange for the delivery, storage, protection and security of Owner-purchased materials, systems and equipment that are a part of the Project until such items are incorporated into the Work.

§ 3.3.24 With the Owner’s maintenance personnel, the Construction Manager shall observe the Contractors’ final testing and start-up of utilities, operational systems and equipment and observe any commissioning as the Contract Documents may require.

§ 3.3.25 When the Construction Manager considers each Contractor’s Work or a designated portion thereof substantially complete, the Construction Manager shall, jointly with that Contractor, prepare for the Architect a list of incomplete or unsatisfactory items and a schedule for their completion. The Construction Manager shall assist the Architect in conducting inspections to determine whether the Work or designated portion thereof is substantially complete.

§ 3.3.26 When the Work of all of the Contractors, or designated portion thereof, is substantially complete, the Construction Manager shall prepare, and the Construction Manager and Architect shall execute, a Certificate of Substantial Completion. The Construction Manager shall submit the executed Certificate to the Owner and Contractors. The Construction Manager shall coordinate the correction and completion of the Work. Following issuance of a Certificate of Substantial Completion of the Work or a designated portion thereof, the Construction Manager shall perform an inspection to confirm the completion of the Work of the Contractors and make recommendations to the Architect when the Work of all of the Contractors is ready for final inspection. The Construction Manager shall assist the Architect in conducting the final inspection.

§ 3.3.27 The Construction Manager shall forward to the Owner, with a copy to the Architect, the following information received from the Contractors: (1) certificates of insurance ; (2) consent of surety or sureties, if any, to reduction in or partial release of retainage or the making of final payment; (3) affidavits, receipts, releases and waivers of liens or bonds indemnifying the Owner against liens; and (4) any other documentation required of the Contractors under the Contract Documents, including warranties and similar submittals.

§ 3.3.28 The Construction Manager shall coordinate receipt, and delivery to the Owner, of other items provided by the Contractors, such as keys, manuals, and record drawings. The Construction Manager shall forward to the Architect a final Project Application for Payment and Project Certificate for Payment, or a final Application for Payment and final Certificate for Payment, upon the Contractors’ compliance with the requirements of the Contract Documents.

§ 3.3.29 Duties, responsibilities and limitations of authority of the Construction Manager as set forth in the Contract Documents shall not be restricted, modified or extended without written consent of the Owner, Construction Manager, Architect, and Contractors. Consent shall not be unreasonably withheld.

§ 3.3.30 Upon request of the Owner, and prior to the expiration of one year from the date of Substantial Completion, the Construction Manager shall, without additional compensation, conduct a meeting with the Owner and Architect to review the facility operations and performance.

# ARTICLE 4   SUPPLEMENTAL AND ADDITIONAL SERVICES

§ 4.1 Supplemental Services

§ 4.1.1 The services listed below are not included in Basic Services but may be required for the Project. The Construction Manager shall provide the listed Supplemental Services only if specifically designated in the table below as the Construction Manager’s responsibility, and the Owner shall compensate the Construction Manager as provided in Section 11.2. Unless otherwise specifically addressed in this Agreement, if neither the Owner nor the Construction Manager is designated, the parties agree that the listed Supplemental Service is not being provided for the Project.

(Designate the Construction Manager’s Supplemental Services and the Owner’s Supplemental Services required for the Project by indicating whether the Construction Manager or Owner shall be responsible for providing the identified Supplemental Service. Insert a description of the Supplemental Services in Section 4.1.2 below or attach the description of services as an exhibit to this Agreement.)

| Supplemental Services | Responsibility (Construction Manager, Owner or not provided) |
| --- | --- |

| § 4.1.1.1 Measured drawings | NP |
| --- | --- |
| § 4.1.1.2 Tenant-related services | NP |
| § 4.1.1.3 Commissioning | NP |
| § 4.1.1.4 Development of a commissioning plan | NP |
| § 4.1.1.5 Sustainable Project Services pursuant to Section 4.1.3 | NP |
| § 4.1.1.6 Furniture, furnishings and equipment delivery, and installation coordination | NP |
| § 4.1.1.7 Furniture, furnishings and equipment procurement assistance | NP |
| § 4.1.1.8 Assistance with site selection | NP |
| § 4.1.1.9 Assistance with selection of the Architect | NP |
| § 4.1.1.10 Furnish land survey | NP |
| § 4.1.1.11 Furnish geotechnical engineering services | NP |
| § 4.1.1.12 Provide insurance advice | NP |
| § 4.1.1.13 Provide supplemental Project risk analysis and mitigation strategies | NP |
| § 4.1.1.14 Stakeholder relationships management | NP |
| § 4.1.1.15 Owner moving coordination | NP |
| § 4.1.1.16 Coordination of Owner’s Separate Contractors | NP |
| § 4.1.1.17 Other Supplemental Services | NP |

§ 4.1.2 Description of Supplemental Services

§ 4.1.2.1 A description of each Supplemental Service identified in Section 4.1.1 as the Construction Manager’s responsibility is provided below.

(Describe in detail the Construction Manager’s Supplemental Services identified in Section 4.1.1 or, if set forth in an exhibit, identify the exhibit.)

TBD

§ 4.1.2.2 A description of each Supplemental Service identified in Section 4.1.1 as the Owner’s responsibility is provided below.

(Describe in detail the Owner’s Supplemental Services identified in Section 4.1.1 or, if set forth in an exhibit, identify the exhibit.)

TBD

§ 4.1.3 If the Owner identified a Sustainable Objective in Article 1, the Construction Manager shall provide, as a Supplemental Service, the Sustainability Services required in AIA Document E235™–2019, Sustainable Projects Exhibit, Construction Manager as Adviser Edition, attached to this Agreement. The Owner shall compensate the Construction Manager as provided in Section 11.2.

§ 4.2 Construction Manager’s Additional Services

§ 4.2.1 The Construction Manager may provide Additional Services after execution of this Agreement, without invalidating this Agreement. Except for services required due to the fault of the Construction Manager, any Additional Services provided in accordance with this Section 4.2 shall entitle the Construction Manager to compensation pursuant to Section 11.3.

§ 4.2.2 Upon recognizing the need to perform the following Additional Services, the Construction Manager shall notify the Owner with reasonable promptness and explain the facts and circumstances giving rise to the need. The Construction Manager shall not proceed to provide the following Additional Services until the Construction Manager receives the Owner’s written authorization:

.1	Services necessitated by a change in the Initial Information, previous instructions or approvals given by the Owner, or a material change in the Project including size, quality, complexity, the Owner’s schedule or budget for Cost of the Work, or procurement or delivery method, or bid packages in addition to those listed in Section 1.1.6. Services necessitated by sections 6.4 and 6.6 shall not be considered additional services;

.2	Services necessitated by the enactment or revision of codes, laws, regulations or official interpretations after the date of this Agreement;

.3	Services necessitated by decisions of the Owner not rendered in a timely manner or any other failure of performance on the part of the Owner or the Owner’s other consultants or contractors;

.4	Preparation of documentation for alternate bid or proposal requests proposed by the Owner;

.5	Preparation for, and attendance at, a public presentation, meeting or hearing;

.6	Preparation for, and attendance at, a dispute resolution proceeding or legal proceeding, except where the Construction Manager is party thereto;

.7	Consultation concerning replacement of Work resulting from fire or other cause during construction and furnishing services required in connection with the replacement of such Work; or

.8	Assistance to the Initial Decision Maker.

§ 4.2.3 To avoid delay in the Construction Phase, the Construction Manager shall provide the following Additional Services, notify the Owner with reasonable promptness, and explain the facts and circumstances giving rise to the need. If, upon receipt of the Construction Manager’s notice, the Owner determines that all or parts of the services are not required, the Owner shall give prompt written notice to the Construction Manager of the Owner’s determination. The Owner shall compensate the Construction Manager for the services provided prior to the Construction Manager’s receipt of the Owner’s notice:

.1	Providing assistance to the Initial Decision Maker in evaluating an extensive number of Claims submitted by a Contractor or others in connection with the Work.

.2	Services required in an emergency to coordinate the activities of a Contractor or Contractors in the event of risk of personal injury or serious property damage, consistent with Section 3.3.15.

§ 4.2.4 Except for services required under Section 3.3.30, Construction Phase Services provided more than 60 days after (1) the date of Substantial Completion of the Work, or (2) the anticipated date of Substantial Completion identified in the Initial Information, whichever is earlier, shall be compensated as Additional Services to the extent the Construction Manager incurs additional cost in providing those Construction Phase Services.

§ 4.2.5 If the services covered by this Agreement have not been completed within forty-eight (48) months of the date of this Agreement, through no fault of the Construction Manager, extension of the Construction Manager’s services beyond that time shall be compensated as Additional Services.

# ARTICLE 5   OWNER’S RESPONSIBILITIES

§ 5.1 Unless otherwise provided for under this Agreement, the Owner shall provide information in a timely manner regarding requirements for and limitations on the Project, including a written program, which shall set forth the Owner’s objectives; schedule; constraints and criteria; special equipment; systems; and site requirements.

§ 5.2 The Owner shall establish the Owner’s budget for the Project, including (1) the budget for the Cost of the Work as defined in Section 6.1; (2) the Owner’s other costs; and (3) reasonable contingencies related to all of these costs. The Owner shall update the Owner’s budget for the Project as necessary throughout the duration of the Project until final completion. If the Owner significantly increases or decreases the Owner’s budget for the Cost of the Work, the Owner shall notify the Construction Manager and Architect. The Owner and the Architect, in consultation with the Construction Manager, shall thereafter agree to a corresponding change in the Project’s scope and quality.

§ 5.3 The Owner acknowledges that accelerated, phased, or fast-track design and construction provides a benefit, but also carries with it the risk of additional costs. If the Owner selects accelerated, phased or fast-track scheduling, the Owner agrees to include in the budget for the Project sufficient contingencies to cover such costs.

§ 5.4 The Owner shall retain an Architect to provide services, duties and responsibilities as described in AIA Document B132–2019, Standard Form of Agreement Between Owner and Architect, Construction Manager as Adviser Edition. The Owner shall provide the Construction Manager with a copy of the scope of services in the agreement executed between the Owner and Architect, and any further modifications to the Architect’s scope of services in the agreement.

§ 5.5 The Owner shall identify a representative authorized to act on the Owner’s behalf with respect to the Project. The Owner shall render decisions pertaining to documents the Construction Manager submits in a timely manner in order to avoid unreasonable delay in the orderly and sequential progress of the Construction Manager’s services.

§ 5.6 Unless provided by the Construction Manager, the Owner shall furnish surveys to describe physical characteristics, legal limitations and utility locations for the site of the Project, and a written legal description of the site. The surveys and legal information shall include, as applicable, grades and lines of streets, alleys, pavements and adjoining property and structures; designated wetlands; adjacent drainage; rights-of-way, restrictions, easements, encroachments, zoning, deed restrictions, boundaries, and contours of the site; locations, dimensions, and other necessary data with respect to existing buildings, other improvements and trees; and information concerning available utility services and lines, both public and private, above and below grade, including inverts and depths. All the information on the survey shall be referenced to a Project benchmark.

§ 5.7 Unless provided by the Construction Manager, the Owner shall furnish services of geotechnical engineers, which may include test borings, test pits, determinations of soil bearing values, percolation tests, evaluations of hazardous materials, seismic evaluation, ground corrosion tests and resistivity tests, including necessary operations for anticipating subsoil conditions, with written reports and appropriate recommendations.

§ 5.8 The Owner shall provide the Supplemental Services designated as the Owner’s responsibility in Section 4.1.1.

§ 5.9 If the Owner identified a Sustainable Objective in Article 1, the Owner shall fulfill its responsibilities as required in AIA Document E235™–2019, Sustainable Projects Exhibit, Construction Manager as Adviser Edition, attached to this Agreement.

§ 5.10 The Owner shall coordinate the services of its own consultants with those services provided by the Construction Manager. Upon the Construction Manager’s request, the Owner shall furnish copies of the scope of services in the contracts between the Owner and the Owner’s consultants. The Owner shall furnish the services of consultants other than those designated as the responsibility of the Construction Manager in this Agreement, or authorize the Construction Manager to furnish them as an Additional Service, when the Construction Manager requests such services and demonstrates that they are reasonably required by the scope of the Project. The Owner shall require that its consultants and contractors maintain insurance, including professional liability insurance, as appropriate to the services or work provided.

§ 5.11 The Owner shall furnish tests, inspections and reports required by law or the Contract Documents, such as structural, mechanical, and chemical tests, tests for air and water pollution, and tests for hazardous materials.

§ 5.12 The Owner shall furnish all legal, insurance and accounting services, including auditing services, that may be reasonably necessary at any time for the Project to meet the Owner’s needs and interests.

§ 5.13 The Owner shall provide prompt written notice to the Construction Manager and Architect if the Owner becomes aware of any fault or defect in the Project, including errors, omissions or inconsistencies in the Architect’s Instruments of Service or any fault or defect in the Construction Manager’s services.

§ 5.14 The Owner reserves the right to perform construction and operations related to the Project with the Owner’s own forces, and to award contracts in connection with the Project which are not part of the Construction Manager’s responsibilities under this Agreement. The Construction Manager shall notify the Owner if any such independent action will interfere with the Construction Manager’s ability to perform the Construction Manager’s responsibilities under this Agreement. When performing construction or operations related to the Project, the Owner agrees to be subject to the same obligations and to have the same rights as the Contractors.

§ 5.15 The Owner shall communicate with the Contractors and the Construction Manager’s consultants through the Construction Manager about matters arising out of or relating to the Contract Documents. The Owner and Construction Manager shall include the Architect in all communications that relate to or affect the Architect’s services or professional responsibilities. The Owner shall promptly notify the Architect of the substance of any direct communications between the Owner and the Construction Manager otherwise relating to the Project. Communications by and with the Architect’s consultants shall be through the Architect.

§ 5.16 Before executing the Contracts for Construction, the Owner shall coordinate the Construction Manager’s duties and responsibilities set forth in the Contracts for Construction with the Construction Manager’s services set forth in this Agreement. The Owner shall provide the Construction Manager a copy of the executed agreements between the Owner and Contractors, including the General Conditions of the Contracts for Construction.

§ 5.17 The Owner shall provide the Construction Manager access to the Project site prior to commencement of the Work and shall obligate the Contractors to provide the Construction Manager access to the Work wherever it is in preparation or progress.

§ 5.18 Within 15 days after receipt of a written request from the Construction Manager, the Owner shall furnish the requested information as necessary and relevant for the Construction Manager to evaluate, give notice of, or enforce lien rights.

# ARTICLE 6   COST OF THE WORK

§ 6.1 For purposes of this Agreement, the Cost of the Work shall be the total cost to the Owner to construct all elements of the Project designed or specified by the Architect and shall include the Contractors’ general conditions costs, overhead and profit. The Cost of the Work also includes the reasonable value of labor, materials, and equipment, donated to, or otherwise furnished by, the Owner. The Cost of the Work includes the compensation of the Construction Manager and Construction Manager’s Consultants during the Construction Phase only, including compensation for reimbursable expenses at the job site, if any. The Cost of the Work does not include the compensation of the Architect; the costs of the land, rights-of-way, financing, or contingencies for changes in the Work; or other costs that are the responsibility of the Owner.

§ 6.2 The Owner’s budget for the Cost of the Work is provided in Initial Information, and shall be adjusted throughout the Project as required under Sections 5.2 and 6.4. Evaluations of the Owner’s budget for the Cost of the Work, and the estimates of the Cost of the Work prepared by the Construction Manager, represent the Construction Manager’s judgment as a person or entity familiar with the construction industry. It is recognized, however, that neither the Construction Manager nor the Owner has control over the cost of labor, materials; or equipment; the Contractors’ methods of determining bid prices; or competitive bidding, market, or negotiating conditions. Accordingly, the Construction Manager cannot and does not warrant or represent that bids or negotiated prices will not vary from the Owner’s budget for the Cost of the Work, or from any estimate of the Cost of the Work, or evaluation, prepared or agreed to by the Construction Manager.

§ 6.3 If the Architect is providing cost estimating services as a Supplemental Service, and a discrepancy exists between the Construction Manager’s cost estimates and the Architect’s cost estimates, the Construction Manager and the Architect shall work together to reconcile the cost estimates.

§ 6.4 If the Construction Manager’s estimate of the Cost of the Work exceeds the Owner’s budget for the Cost of the Work, the Construction Manager, in consultation with the Architect, shall make appropriate recommendations to the Owner to adjust the Project’s size, quality, or budget for the Cost of the Work, and the Owner shall cooperate with the Construction Manager and Architect in making such adjustments.

§ 6.5 If the Construction Manager’s estimate of the Cost of the Work exceeds the Owner’s budget for the Cost of the Work, the Owner shall

.1	give written approval of an increase in the budget for the Cost of the Work;

.2	terminate in accordance with Section 9.5;

.3	in consultation with the Construction Manager and Architect, revise the Project program, scope, or quality as required to reduce the Cost of the Work; or

.4	implement any other mutually acceptable alternative.

§ 6.6 If the Owner chooses to revise the Project program, scope, or quality to reduce the Cost of the Work pursuant to Section 6.5.3, or if the bids or proposals received from the prospective Contractors, in the aggregate, exceed the Owner’s budget for the Cost of the Work, and the Owner chooses to revise the Project program, scope, or quality to reduce the Cost of the Work , the Construction Manager shall cooperate with the Owner and Architect to develop the necessary revisions, update the cost estimate, and obtain additional bids. The Construction Manager will perform the services described in Sections 6.4 and 6.6 without additional compensation.

# ARTICLE 7   COPYRIGHTS AND LICENSES

The Construction Manager and the Construction Manager’s consultants, if any, shall not own or claim a copyright in the Instruments of Service. The Construction Manager, the Construction Manager’s consultants, if any, and the Owner warrant that in transmitting Instruments of Service, or any other information, the transmitting party is the copyright owner of such information or has permission from the copyright owner to transmit such information for its use on the Project.

# ARTICLE 8   CLAIMS AND DISPUTES

§ 8.1 General

§ 8.1.1 The Owner and Construction Manager shall commence all claims and causes of action against the other and arising out of or related to this Agreement, whether in contract, tort, or otherwise, in accordance with the requirements of the binding dispute resolution method selected in this Agreement and within the period specified by applicable law, but in any case not more than 10 years after the date of Substantial Completion of the Work. The Owner and Construction Manager waive all claims and causes of action not commenced in accordance with this Section 8.1.1.

§ 8.1.2 To the extent damages are covered by property insurance, the Owner and Construction Manager waive all rights against each other and against the contractors, consultants, agents, and employees of the other for damages, except such rights as they may have to the proceeds of such insurance as set forth in AIA Document A232–2019, General Conditions of the Contract for Construction. The Owner or the Construction Manager, as appropriate, shall require of the contractors, consultants, agents, and employees of any of them, similar waivers in favor of the other parties enumerated herein.

§ 8.1.3 The Construction Manager shall indemnify and hold the Owner and the Owner’s officers and employees harmless from and against damages, losses and judgments arising from claims by third parties, including reasonable attorneys’ fees and expenses recoverable under applicable law, but only to the extent they are caused by the negligent acts or omissions of the Construction Manager, its employees and its consultants in the performance of professional services under this Agreement. The Construction Manager’s obligation to indemnify and hold the Owner and the Owner’s officers and employees harmless does not include a duty to defend. The Construction Manager’s duty to indemnify the Owner under this Section 8.1.3 shall be limited to the available proceeds of the insurance coverage required by this Agreement.

§ 8.1.4 The Construction Manager and Owner waive consequential damages for claims, disputes, or other matters in question, arising out of or relating to this Agreement. This mutual waiver is applicable, without limitation, to all consequential damages due to either party’s termination of this Agreement, except as specifically provided in Section 9.7.

§ 8.2 Mediation

§ 8.2.1 Any claim, dispute or other matter in question arising out of or related to this Agreement shall be subject to mediation as a condition precedent to binding dispute resolution. If such matter relates to or is the subject of a lien arising out of the Construction Manager’s services, the Construction Manager may proceed in accordance with applicable law to comply with the lien notice or filing deadlines prior to resolution of the matter by mediation or by binding dispute resolution.

§ 8.2.2 The Owner and Construction Manager shall endeavor to resolve claims, disputes and other matters in question between them by mediation, which, unless the parties mutually agree otherwise, shall be administered by the American Arbitration Association in accordance with its Construction Industry Mediation Procedures in effect on the date of this Agreement. A request for mediation shall be made in writing, delivered to the other party to this Agreement, and filed with the person or entity administering the mediation. The request may be made concurrently with the filing of a complaint or other appropriate demand for binding dispute resolution but, in such event, mediation shall proceed in advance of binding dispute resolution proceedings, which shall be stayed pending mediation for a period of 60 days from the date of filing, unless stayed for a longer period by agreement of the parties or court order. If an arbitration proceeding is stayed pursuant to this section, the parties may nonetheless proceed to the selection of the arbitrator(s) and agree upon a schedule for later proceedings.

§ 8.2.3 The parties shall share the mediator’s fee and any filing fees equally. The mediation shall be held in the place where the Project is located, unless another location is mutually agreed upon. Agreements reached in mediation shall be enforceable as settlement agreements in any court having jurisdiction thereof.

§ 8.2.4 If the parties do not resolve a dispute through mediation pursuant to this Section 8.2, the method of binding dispute resolution shall be the following:

(Check the appropriate box.)

[ «  » ]	Arbitration pursuant to Section 8.3 of this Agreement

[ X]	Litigation in a court of competent jurisdiction

[ «  » ]	Other: (Specify)

If the Owner and Construction Manager do not select a method of binding dispute resolution, or do not subsequently agree in writing to a binding dispute resolution method other than litigation, the dispute will be resolved in a court of competent jurisdiction.

§ 8.3 Arbitration

§ 8.3.1 If the parties have selected arbitration as the method for binding dispute resolution in this Agreement, any claim, dispute or other matter in question arising out of or related to this Agreement subject to, but not resolved by, mediation shall be subject to arbitration, which, unless the parties mutually agree otherwise, shall be administered by the American Arbitration Association in accordance with its Construction Industry Arbitration Rules in effect on the date of this Agreement. A demand for arbitration shall be made in writing, delivered to the other party to this Agreement, and filed with the person or entity administering the arbitration.

§ 8.3.1.1 A demand for arbitration shall be made no earlier than concurrently with the filing of a request for mediation, but in no event shall it be made after the date when the institution of legal or equitable proceedings based on the claim, dispute or other matter in question would be barred by the applicable statute of limitations. For statute of limitations purposes, receipt of a written demand for arbitration by the person or entity administering the arbitration shall constitute the institution of legal or equitable proceedings based on the claim, dispute or other matter in question.

§ 8.3.2 The foregoing agreement to arbitrate, and other agreements to arbitrate with an additional person or entity duly consented to by parties to this Agreement, shall be specifically enforceable in accordance with applicable law in any court having jurisdiction thereof.

§ 8.3.3 The award rendered by the arbitrator(s) shall be final, and judgment may be entered upon it in accordance with applicable law in any court having jurisdiction thereof.

§ 8.3.4 Consolidation or Joinder

§ 8.3.4.1 Either party, at its sole discretion, may consolidate an arbitration conducted under this Agreement with any other arbitration to which it is a party provided that (1) the arbitration agreement governing the other arbitration permits consolidation; (2) the arbitrations to be consolidated substantially involve common questions of law or fact; and (3) the arbitrations employ materially similar procedural rules and methods for selecting arbitrator(s).

§ 8.3.4.2 Either party, at its sole discretion, may include by joinder persons or entities substantially involved in a common question of law or fact whose presence is required if complete relief is to be accorded in arbitration, provided that the party sought to be joined consents in writing to such joinder. Consent to arbitration involving an additional person or entity shall not constitute consent to arbitration of any claim, dispute or other matter in question not described in the written consent.

§ 8.3.4.3 The Owner and Construction Manager grant to any person or entity made a party to an arbitration conducted under this Section 8.3, whether by joinder or consolidation, the same rights of joinder and consolidation as the Owner and Construction Manager under this Agreement.

§ 8.4 The provisions of this Article 8 shall survive the termination of this Agreement.

# ARTICLE 9   TERMINATION OR SUSPENSION

§ 9.1 If the Owner fails to make payments to the Construction Manager in accordance with this Agreement, such failure shall be considered substantial nonperformance and cause for termination or, at the Construction Manager’s option, cause for suspension of performance of services under this Agreement. If the Construction Manager elects to suspend services, the Construction Manager shall give seven days’ written notice to the Owner before suspending services. In the event of a suspension of services, the Construction Manager shall have no liability to the Owner for delay or damage caused the Owner because of such suspension of services. Before resuming services, the Owner shall pay the Construction Manager all sums due prior to suspension and any expenses incurred in the interruption and resumption of the Construction Manager’s services. The Construction Manager’s fees for the remaining services and the time schedules shall be equitably adjusted.

§ 9.2 If the Owner suspends the Project, the Construction Manager shall be compensated for services performed prior to notice of such suspension. When the Project is resumed, the Construction Manager shall be compensated for expenses incurred in the interruption and resumption of the Construction Manager’s services. The Construction Manager’s fees for the remaining services and the time schedules shall be equitably adjusted.

§ 9.3 If the Owner suspends the Project for more than 90 cumulative days for reasons other than the fault of the Construction Manager, the Construction Manager may terminate this Agreement by giving not less than seven days’ written notice.

§ 9.4 Either party may terminate this Agreement upon not less than seven days’ written notice should the other party fail substantially to perform in accordance with the terms of this Agreement through no fault of the party initiating the termination.

§ 9.5 The Owner may terminate this Agreement upon not less than seven days’ written notice to the Construction Manager for the Owner’s convenience and without cause.

§ 9.6 If the Owner terminates this Agreement for its convenience pursuant to Section 9.5, or the Construction Manager terminates this Agreement pursuant to Section 9.3, the Owner shall compensate the Construction Manager for services performed prior to termination, Reimbursable Expenses incurred, and costs attributable to termination, including the costs attributable to the Construction Manager’s termination of consultant agreements.

§ 9.7 In addition to any amounts paid under Section 9.6, if the Owner terminates this Agreement for its convenience pursuant to Section 9.5, or the Construction Manager terminates this Agreement pursuant to Section 9.3, the Owner shall pay to the Construction Manager the following termination fee:

(Set forth below the amount of any termination fee, or the method for determining any termination fee.)

None

§ 9.8 Except as otherwise expressly provided herein, this Agreement shall terminate one year from the date of Substantial Completion.

# ARTICLE 10   MISCELLANEOUS PROVISIONS

§ 10.1 This Agreement shall be governed by the law of the place where the Project is located, excluding that jurisdiction’s choice of law rules. If the parties have selected arbitration as the method of binding dispute resolution, the Federal Arbitration Act shall govern Section 8.3.

§ 10.2 Terms in this Agreement shall have the same meaning as those in AIA Document A232–2019, General Conditions of the Contract for Construction, except for purposes of this Agreement, the term “Work” shall include the work of all Contractors under the administration of the Construction Manager and the Architect.

§ 10.3 The Owner and Construction Manager, respectively, bind themselves, their agents, successors, assigns, and legal representatives to this Agreement. Neither the Owner nor the Construction Manager shall assign this Agreement without the written consent of the other, except that the Owner may assign this Agreement to a lender providing financing for the Project if the lender agrees to assume the Owner’s rights and obligations under this Agreement, including any payments due to the Construction Manager by the Owner prior to the assignment.

§ 10.4 If the Owner requests the Construction Manager to execute certificates, the proposed language of such certificates shall be submitted to the Construction Manager for review at least 14 days prior to the requested dates of execution. If the Owner requests the Construction Manager to execute consents reasonably required to facilitate assignment to a lender, the Construction Manager shall execute all such consents that are consistent with this Agreement, provided the proposed consent is submitted to the Construction Manager for review at least 14 days prior to execution. The Construction Manager shall not be required to execute certificates or consents that would require knowledge, services, or responsibilities beyond the scope of this Agreement.

§ 10.5 Nothing contained in this Agreement shall create a contractual relationship with, or a cause of action in favor of, a third party against either the Owner or Construction Manager.

§ 10.6 Unless otherwise required in this Agreement, the Construction Manager shall have no responsibility for the discovery, presence, handling, removal or disposal of, or exposure of persons to, hazardous materials or toxic substances in any form at the Project site.

§ 10.7 The Construction Manager shall have the right to include photographic or artistic representations of the design of the Project among the Construction Manager’s promotional and professional materials. The Construction Manager shall provide professional credit for the Architect and the Contractors in the Construction Manager’s promotional materials for the Project. The Construction Manager shall be given reasonable access to the completed Project to make such representations. However, the Construction Manager’s materials shall not include the Owner’s confidential or proprietary information if the Owner has previously advised the Construction Manager in writing of the specific information considered by the Owner to be confidential or proprietary. The Owner shall provide professional credit for the Construction Manager in the Owner’s promotional materials for the Project. This Section 10.7 shall survive the termination of this Agreement unless the Owner terminates this Agreement for cause pursuant to Section 9.4.

§ 10.8 If the Construction Manager or Owner receives information specifically designated as “confidential” or “business proprietary,” the receiving party shall keep such information strictly confidential and shall not disclose it to any other person except as set forth in Section 10.8.1. This Section 10.8 shall survive the termination of this Agreement.

§ 10.8.1 The receiving party may disclose "confidential" or "business proprietary" information after 7 days’ notice to the other party, when required by law, arbitrator’s order, or court order, including a subpoena or other form of compulsory legal process issued by a court or governmental entity, or to the extent such information is reasonably necessary for the receiving party to defend itself in any dispute. The receiving party may also disclose such information to its employees, consultants, or contractors in order to perform services or work solely and exclusively for the Project, provided those employees, consultants and contractors are subject to the restrictions on the disclosure and use of such information as set forth in this Section 10.8.

§ 10.9 The invalidity of any provision of the Agreement shall not invalidate the Agreement or its remaining provisions. If it is determined that any provision of the Agreement violates any law, or is otherwise invalid or unenforceable, then that provision shall be revised to the extent necessary to make that provision legal and enforceable. In such case the Agreement shall be construed, to the fullest extent permitted by law, to give effect to the parties’ intentions and purposes in executing the Agreement.

# ARTICLE 11   COMPENSATION

§ 11.1 For the Construction Manager’s Basic Services described under Article 3, the Owner shall compensate the Construction Manager as follows:

§ 11.1.1 For Preconstruction Phase Services in Section 3.2:

(Insert amount of, or basis for, compensation, including stipulated sums, multiples or percentages.)

LIST FEES PER PHASE OR ESTIMATE

§ 11.1.2 For Construction Phase Services in Section 3.3:

(Insert amount of, or basis for, compensation, including stipulated sums, multiples or percentages.)

% of the Cost of Work

§ 11.2 For the Construction Manager’s Supplemental Services designated in Section 4.1.1, and for any Sustainability Services required pursuant to Section 4.1.3, the Owner shall compensate the Construction Manager as follows:

(Insert amount of, or basis for, compensation. If necessary, list specific services to which particular methods of compensation apply.)

TBD

§ 11.3 For Additional Services that may arise during the course of the Project, including those under Section 4.2, the Owner shall compensate the Construction Manager as follows:

(Insert amount of, or basis for, compensation.)

TBD

§ 11.4 Compensation for Supplemental and Additional Services of the Construction Manager’s consultants when not included in Sections 11.2 or 11.3, shall be the amount invoiced to the Construction Manager plus «  » percent ( «  » %), or as follows:

(Insert amount of, or basis for computing, Construction Manager’s consultants’ compensation for Supplemental or Additional Services.)

N/A

§ 11.5 The hourly billing rates for services of the Construction Manager and the Construction Manager’s consultants are set forth below. The rates shall be adjusted in accordance with the Construction Manager’s and Construction Manager’s consultants’ normal review practices.

(If applicable, attach an exhibit of hourly billing rates or insert them below.)

| Employee or Category | Rate ($0.00) |
| --- | --- |
| Project Executive | RATES |
| Project Manager |  |
| Administrative Assistant |  |
| Sr. Superintendent |  |
| Safety Manager |  |
| Forman |  |
| Project Engineer/Surveyor MEP Coordinator Fuel per Manager on site full time Vehicles per manager on site full time Living Allowance per Superintendent on site full time |  |

§ 11.6 Compensation for Reimbursable Expenses

§ 11.6.1 Reimbursable Expenses are in addition to compensation for Basic, Supplemental, and Additional Services and include expenses incurred by the Construction Manager and the Construction Manager’s consultants directly related to the Project, as follows:

.1	Transportation and authorized out-of-town travel and subsistence;

.2	Long distance services, dedicated data and communication services, teleconferences, Project web sites, and extranets;

.3	Permitting and other fees required by authorities having jurisdiction over the Project;

.4	Printing, reproductions, plots, and standard form documents;

.5	Postage, handling, and delivery;

.6	Expense of overtime work requiring higher than regular rates, if authorized in advance by the Owner;

.7	Professional photography, and presentation materials requested by the Owner;

.8	If required by the Owner, and with the Owner’s prior written approval, the Construction Manager’s consultants’ expenses of professional liability insurance dedicated exclusively to this Project, or the expense of additional insurance coverage or limits in excess of that normally maintained by the Construction Manager’s consultants;

.9	All taxes levied on professional services and on reimbursable expenses;

.10	Site office expenses; and

.11	Other similar Project-related expenditures.

§ 11.6.2 For Reimbursable Expenses the compensation shall be the expenses incurred by the Construction Manager and the Construction Manager’s consultants plus «XX percent ( «%» %) of the expenses incurred.

§ 11.7 Construction Manager’s Insurance. If the types and limits of coverage required in Section 2.8 are in addition to the types and limits the Construction Manager normally maintains, the Owner shall pay the Construction Manager for the additional costs incurred by the Construction Manager for the additional coverages as set forth below.

(Insert the additional coverages the Construction Manager is required to obtain in order to satisfy the requirements set forth in Section 2.8, and for which the Owner shall reimburse the Construction Manager.)

N/A

§ 11.8 Payments to the Construction Manager

§ 11.8.1 Initial Payment

§ 11.8.1.1 An initial payment of « zero ($ «0.00» ) shall be made upon execution of this Agreement and is the minimum payment under this Agreement. It shall be credited to the Owner’s account in the final invoice.

§ 11.8.2 Progress Payments

§ 11.8.2.1 Unless otherwise agreed, payments for services shall be made monthly in proportion to services performed. Payments are due and payable upon presentation of the Construction Manager’s invoice. Amounts unpaid «forty-five» ( «45» ) days after the invoice date shall bear interest at the rate entered below, or in the absence thereof at the legal rate prevailing from time to time at the principal place of business of the Construction Manager.

(Insert rate of monthly or annual interest agreed upon.)

Interest shall be calculated at the rate of one and one-half percent in accordance with Miss. Code Ann Section 31-7-305.

§ 11.8.2.2 The Owner shall not withhold amounts from the Construction Manager’s compensation to impose a penalty or liquidated damages on the Construction Manager, or to offset sums requested by or paid to Contractors for the cost of changes in the Work, unless the Construction Manager agrees or has been found liable for the amounts in a binding dispute resolution proceeding.

§ 11.8.2.3 Records of Reimbursable Expenses, expenses pertaining to Supplemental and Additional Services, and services performed on the basis of hourly rates shall be available to the Owner at mutually convenient times.

# ARTICLE 12   SPECIAL TERMS AND CONDITIONS

Special terms and conditions that modify this Agreement are as follows:

(Include other terms and conditions applicable to this Agreement.)

Exhibit A – Mississippi State University Supplementary Conditions to AIA Document C132-2019 and AIA A232-2019.

# ARTICLE 13   SCOPE OF THE AGREEMENT

§ 13.1 This Agreement represents the entire and integrated agreement between the Owner and the Construction Manager and supersedes all prior negotiations, representations or agreements, either written or oral. This Agreement may be amended only by written instrument signed by both the Owner and Construction Manager.

§ 13.2 This Agreement is comprised of the following documents identified below:

.1	AIA Document C132™–2019, Standard Form Agreement Between Owner and Construction Manager as Adviser

.3	Exhibits:

(Check the appropriate box for any exhibits incorporated into this Agreement.)

[ «X» ]	Other Exhibits incorporated into this Agreement:

(Clearly identify any other exhibits incorporated into this Agreement, including any exhibits identified in Section 4.1.2.)

Exhibit A, Mississippi State University Supplementary Conditions to AIA Document C132-2019 and AIA A232-2019

.4	Other documents:

(List other documents, if any, forming part of the Agreement.)

None

This Agreement is entered into as of the day and year first written above.

| OWNER (Signature) |  | CONSTRUCTION MANAGER (Signature) |
| --- | --- | --- |
| « »« » |  | «CMA, »«President» |
| (Printed name and title) |  | (Printed name and title) |

The following Supplementary Conditions supplement, modify, change, delete from, or add to the Standard Form of Agreement Between Owner and Construction Manager as Adviser, AIA Document C132 - 2019 and General Conditions of the Contract for Construction, AIA Document A232-2019. When any Article of the AIA C132-2019 or AIA 232-2019 is not modified, added to, or deleted, by these Supplementary Conditions, the unaltered provisions of that Article, Paragraph, Subparagraph, or Clause will remain in effect. These Supplementary Conditions shall be Conditions of the Contract. If any conflict or inconsistency exists between these Supplementary Conditions and AIA C132-2019 or the AIA A232-2019, these Supplementary Conditions control.

PART I  SUPPLEMENTARY CONDITIONS TO C132-2019

Article 1  	INITIAL INFORMATION

No supplementary conditions.

Article 2 	CONSTRUCTION MANAGER’S RESPONSIBILITIES

2.6	Delete this paragraph in its entirety and replace with the following:

The Construction Manager has notified the Owner in writing of the names and qualifications of its proposed key staff members. The Construction Manager shall not staff any employee on the Project to whom the Owner has made reasonable and timely objection. The Construction Manager shall not change its key staff members without Owner’s express consent, which shall not be unreasonably withheld or delayed.

2.8	Delete this paragraph and replace it with the following:

2.8.1	Construction Manager shall purchase and maintain in full force and effect such insurance in accordance with the limits defined in Exhibit A-1, as will protect itself,  the Owner, and the Board of Trustees of State Institutions of Higher Learning (IHL), and their employees, officers, agents, directors, and trustees, from claims, for, including but not limited to, bodily injury, personal injury, wrongful death, and property damage, which may arise out of or result from the Project. Such insurance coverage shall include, without limitation, coverage for claims arising from the acts or omissions of Construction Manager or a subcontractor of Construction Manager, by anyone directly or indirectly employed or engaged by any of them, or by anyone for whose acts any of them may be liable. The amounts of such insurance and any additional insurance requirements are specified in Exhibit A-1.

2.8.2 The following policies and coverages shall be furnished by Construction Manager:

2.8.2.1		COMMERCIAL FORM GENERAL LIABILITY INSURANCE covering all work done by or on behalf of Construction Manager and providing insurance for bodily injury, wrongful death, personal injury, property damage, and contractual liability. Except with respect to bodily injury and property damage included within the products and completed operations hazards, the aggregate limit shall apply separately to work required of Construction Manager in the Contract Documents. If the insurance coverage is written on a claims-made form, coverage shall continue for a period of not less than 6 years following termination of the Contract. Coverage shall provide for a retroactive date of placement prior to or coinciding with the effective date of this Contract. Construction Manager shall also require all of its subcontractors to maintain this insurance coverage.

2.8.2.2		BUSINESS AUTOMOBILE LIABILITY INSURANCE on an “Occurrence” form covering owned, hired, leased, and non-owned automobiles used by or on behalf of Construction Manager and providing insurance for bodily injury and property damage. Construction Manager shall also require all of its subcontractors to maintain this insurance coverage.

2.8.2.3		WORKERS’ COMPENSATION as required by Federal and State of Mississippi law AND EMPLOYER’S LIABILITY INSURANCE. Construction Manager shall also require all of its subcontractors to maintain this insurance coverage.

2.8.2.4		PROFESSIONAL LIABILITY INSURANCE covering, without limitation, negligent acts, errors, and/or omissions in the performance of professional services. If professional liability insurance is written on a claims-made form, coverage shall continue for a period of not less than 6 years following termination of this Contract. Coverage shall provide for a retroactive date of placement prior to or coinciding with the effective date of this Contract.

2.8.2.5		EXCESS LIABILITY UMBRELLA POLICY INSURANCE.

2.8.3	 Certificates of Insurance, as evidence of the insurance required by the Contract Documents and as further required by Exhibit A-1, shall be submitted by Construction Manager to Owner prior to execution of the Contract. The Certificates of Insurance shall provide evidence of notice of cancellation notices which provide for no cancellation or modification of coverage without prior written notice to Owner, in accordance with policy provisions.

2.8.4 	In the event Construction Manager does not comply with these insurance requirements, Owner may, at its option, provide insurance coverage to protect itself, IHL, and their employees, offices, agents, directors, and trustees; and the cost of such insurance shall be paid by Construction Manager and may be deducted from the contract amount.

2.8.5 Construction Manager’s insurance as required by this Article shall, by endorsement to the policies, include the following:

2.8.5.1		Mississippi State University, and IHL, and each of their representatives, consultants, officers, agents, employees, directors, and trustees, regardless of whether or not identified in the Contract Documents or to the Construction Manager in writing, will be included as additional named insureds on all required insurance policies for and relating to the Project. This requirement shall not apply to Worker’s Compensation and Employer’s Liability insurance.

2.8.5.2		A Severability of Interest Clause that shall be primary insurance as respects the Owner, IHL, their officers, agents, directors, trustees, and employees. Any insurance or self-insurance maintained by the Owner, the University, or IHL shall be in excess of and non-contributory to the insurances of the Construction Manager. The provision shall state that, “The term ‘insured’ is hereby used severally and not collectively, but the inclusion herein of more than one insured shall not operate to increase the limits of the insurers’ liability.”

2.8.5.3		The Owner, IHL, University’s consultants, University’s representatives, and University’s representative’s consultants will not by reason of their inclusion as insureds incur liability to the insurance carriers for payment of premiums for such insurance.

2.8.5.4		All insurances provided by Construction Manager shall include waivers of subrogation in favor of the University, the Design Professional, and IHL.

2.8.6	The form and substance of all insurance policies required to be obtained by Construction Manager shall be subject to approval by the Owner. All policies required by this Article shall be issued by companies with Best rating of A- or better, and a financial classification of VIII or better (or an equivalent rating by Standard & Poor or Moody’s) or (ii) guaranteed, under terms consented to by the University (such consent to not be unreasonably withheld), by companies with a Best rating of A- or better, and a financial classification of VIII or better (or an equivalent rating by Standard & Poor or Moody’s).

2.8.7	Construction Manager shall, by mutual agreement with the Owner, furnish any additional insurance as may be required by University or IHL. Construction Manager shall provide Certificates of Insurance evidencing such additional insurance.

2.8.8	The Certificate of Insurance shall show (1) all companies affording coverage and (2) the name of the insured. The name of the insured must be the name under which the entity is licensed by the Contractors State License Board.

2.8.9	 At the request of the University or IHL, Construction Manager shall submit to University copies of the policies obtained by Construction Manager.

2.8.10 	Construction Manager shall require all subcontractors to provide insurance meeting the requirements of Exhibit A-1 in amounts up to and including the limits specified in Exhibit A-1.

2.12	Add a new paragraph as follows:

The Construction Manager shall comply with the Mississippi Employment Protection Act in accordance with Section 71-11-3 of the Mississippi Code 1972, annotated. The Construction Manager further agrees to maintain records of such compliance, and upon request of the University to provide a copy of each such verification to the University.

Article 3	SCOPE OF CONSTRUCTION MANAGER’S BASIC SERVICES

3.2.15 	Delete this subparagraph in its entirety.

3.2.19	Add the following to the end of this subparagraph:

All services provided by Construction Manager under this subparagraph shall be subject to and in compliance with applicable Mississippi bid laws and the procurement policies and procedures the Owner.

3.2.20	Delete this subparagraph in its entirety.

3.3.20	Delete this subparagraph in its entirety and replace with the following:

In collaboration with the Architect and Contractors, the Construction Manager shall establish and implement written procedures to assist in expediting the processing and approval of shop drawings, product data, samples and other submittals by the Contractors and Architect.  The Construction Manager is not required to review or approve such items but shall consult with the Owner about such items upon request by the Owner.

3.3.21.3 Delete this subparagraph in its entirety.

Article 4	SUPPLEMENTAL AND ADDITIONAL SERVICES

4.2.4	Delete this subparagraph in its entirety.

Article 5	OWNER’S RESPONSIBILITIES

5.6	Delete this subparagraph in its entirety.

5.7 	Delete this subparagraph in its entirety and replace with the following:

The Architect shall furnish services of geotechnical engineers, which may include test borings, test pits, determination of soil bearing values, percolation tests, evaluations of hazardous materials, seismic evaluations, ground corrosion tests and resistivity tests, including necessary operations for anticipating subsoil conditions, with written reports and appropriate recommendations.

5.11	Delete this subparagraph in its entirety and replace with the following:

The Architect shall furnish tests, inspections and reports required by law or the Contract Documents, such as structural, mechanical, and chemical tests, tests for air and water pollution, and test for hazardous materials.

Article 6	COST OF THE WORK

6.6	Delete the last sentence of this subparagraph.

Article 7	COPYRIGHTS AND LICENSES

Add a new sentence at the end of this Article:

This Paragraph in no way supersedes the Owner’s document rights set forth in the Agreement between the Owner and the Professional.

Article 8	CLAIMS AND DISPUTES

8.1.1.	Delete this subparagraph in its entirety.

8.1.2 	Delete this subparagraph in its entirety.

8.1.4	Delete this subparagraph in its entirety.

8.1.3	Delete this subparagraph and replace it with the following:

The Construction Manager shall defend, hold harmless, and indemnify the Owner, IHL, and each of their representatives, consultants, officers, agents, employees, directors, and trustees against all claims, demands, damages, losses, or judgments, including reasonable attorneys’ fees and expenses, caused in whole or in part by the negligent acts or omissions of the Construction Manager, one of its subcontractors, or one of their employees, officers, representatives, or agents.

8.2.	Delete this paragraph in its entirety.

8.3.	Delete this paragraph in its entirety.

Article 9	TERMINATION OR SUSPENSION

9.4	Delete this subparagraph and replace it with the following:

Either party may terminate this Agreement upon not less than seven days’ written notice should the other party fail substantially to perform in accordance with the terms of this Agreement through no fault of the party initiating the termination, provided that the party initiating the termination must provide written notice of the failure and an opportunity to commence a cure with ten (10) days of receipt of such notice.

9.5	Replace “seven days written notice” with “thirty days written notice”.

9.6	Delete this paragraph and replace with the following:

If the Owner terminates this Agreement for its convenience pursuant to Section 9.5, or the Construction Manager terminates this Agreement pursuant to Section 9.3, or either party terminates this Agreement pursuant to Section 9.4, the Owner shall compensate the Construction Manager for services performed prior to termination, Reimbursable Expenses incurred, and costs attributable to termination, including the costs attributable to the Construction Manager’s termination of consultant agreements.

Article 10 	MISCELLANEOUS PROVISIONS

10.1	GOVERNING LAW:	Change this Title and Paragraph to read as follows:

GOVERNING LAW AND VENUE

The Contract shall be governed by the laws of the State of Mississippi. The courts of Oktibbeha County, Mississippi shall be the sole and exclusive jurisdiction and venue for any civil action related to this Agreement.

Article 11 	COMPENSATION

11.6.1.6  This subparagraph is deleted in its entirety.

11.6.1.8 This subparagraph is deleted in its entirety.

11.6.1.9  This subparagraph is deleted in its entirety.

11.6.1.11 Delete this subparagraph and replace with the following:

Other similar Project-related expenditures approved by the Owner.

11.6.2  Delete this subparagraph and replace it with the following:

For Reimbursable Expenses under 11.6.1, the compensation shall be the expenses incurred by the Construction Manager and the Construction Manager’s approved consultants with ten percent (10%) markup of the expenses incurred.

11.7	This paragraph is deleted in its entirety.

11.8.1.1	 This subparagraph is deleted in its entirety.

Article 12	SPECIAL TERMS AND CONDITIONS

No supplementary conditions.

Article 13	SCOPE OF THE AGREEMENT

13.2.2.  This subparagraph is deleted in its entirety.

Part II	SUPPLEMENTARY CONDITIONS TO A232-2019

Article 1   GENERAL PROVISIONS

  - Basic Definitions

1.1.1 	Delete the last sentence of the subparagraph and substitute the following sentence:

The Contract Documents include Advertisements for Bids, Instructions to Bidders, Proposal Form, sample forms and all portions of addenda issued prior to execution of the Contract.

1.5	OWNERSHIP AND USE OF DRAWINGS, SPECIFICATIONS AND OTHER INSTRUMENTS OF SERVICE

1.5.1	Add a new sentence at the end of this Subparagraph:

This Paragraph in no way supersedes the Owner’s document rights set forth in the Agreement between the Owner and the Professional.

Article 2  OWNER

No Supplementary Conditions.

Article 3  CONTRACTOR

  - LABOR AND MATERIALS

3.4.4	Add a new subparagraph as follows:

The Contractor shall comply with the Mississippi Employment Protection Act in accordance with Section 71-11-3 of the Mississippi Code 1972, annotated. The Contractor further agrees to maintain records of such compliance, and upon request of the University to provide a copy of each such verification to the University.

3.9	SUPERINTENDENT

3.9.1	Add the following new subparagraphs as follows:

General:  Provide minimum administrative and supervisory personnel as follows:

- Minimum Contractor Staffing Requirements:  Contractor will provide qualified staff for the following positions during the project as outlined below. Superintendents cannot perform the roles of two concurrent positions, but can transition to a subsequent role when work is substantially complete.

  - Project Superintendent – minimum 5 years commercial experience; on site full time for all buildings; assigned to the project from initial mobilization through substantial completion and punch list.

  - Project Manager –minimum 7 years commercial experience.

  - Quality Control and Scheduling Manager –minimum 5 years commercial experience.

Submit all resumes within 10 days of Notice of Award of Contract.

After Owner’s approval of the superintendents, none shall be replaced by the Contractor without the Owner’s consent, unless the Contractor submits evidence that a superintendent should be terminated for cause.

All Contractor superintendents personnel must have minimum 30-hour OSHA training certification.

The Contractor is required to maintain a dedicated superintendent for phases of the work that are behind schedule or experiencing quality or safety issues.

The MEP subcontractors shall provide a full force of superintendents for the duration of the project.

3.9.2	Change the second line in this Subparagraph to read as follows:

The Architect through the Construction Manager shall, within a reasonable time, notify the Contractor in writing of any objection to the proposed superintendent.

3.18	INDEMNIFICATION

Any reference to “Owner” throughout Paragraph 3.18 shall include a reference to:

Mississippi State University, the Board of Trustees of State Institutions of Higher Learning, and their employees, representatives, agents, and trustees.

3.18.3	Add a new Subparagraph as follows:

The Contractor agrees to defend, hold harmless and indemnify the Owner against all claims or demands caused in whole or in part by the Contractor’s acts or omissions.

Article 4 ARCHITECT Change this Title and Paragraph to read as follows:

ARCHITECT AND CONSTRUCTION MANAGER

  - ADMINISTRATION OF THE CONTRACT

4.2.1	Change the first line of this Subparagraph to read as follows:

The Construction Manager and Architect will provide administration of the Contract as described in the Contract Documents, and will be the Owner’s representative (1) during construction, (2) until the final payment is due and (3) with the Owner’s concurrence, from time to time during the one year period for correction of Work described in Section 12.2.

Article 5 SUBCONTRACTORS

5.2	AWARD OF SUBCONTRACTS AND OTHER CONTRACTS FOR PORTIONS OF THE WORK

5.2.1	Change the first line of this Subparagraph to read as follows:

Unless otherwise stated in the Contract Documents or the bidding requirements, the Contractor, within 7 days after written notice by the Architect of award of the Contract by the Owner, shall furnish in writing to the Construction Manager for review by the Owner, Construction Manager and the Architect the names of persons or entities (including those who are to furnish materials or equipment fabricated to a special design) proposed for each principal portion of the Work.

Article 6  CONSTRUCTION BY OWNER OR BY SEPARATE CONTRACTORS

No supplementary conditions.

Article 7  CHANGES IN THE WORK

  - CHANGE ORDERS

7.2.2	Add a new Subparagraph as follows:

The maximum cost included in a Change Order for profit and overhead is limited to fifteen percent (15%) of the total of the actual cost for materials, labor and subcontracts. Profit and overhead include: all taxes, fees, permits, insurance, bond, job superintendent, job and home office expense. All Subcontractors shall acquiesce to the same requirements when participating in a Change Order.

  - CONSTRUCTION CHANGE DIRECTIVES

7.3.9	Delete this Subparagraph in its entirety.

Article 8  TIME

8.1	DEFINITIONS

8.1.2	Change this Subparagraph to read as follows:

The date of commencement of the Work is the date established in the Notice to Proceed.

8.3	DELAYS AND EXTENSIONS OF TIME

8.3.1	Change this Subparagraph to read as follows:

If the Contractor is delayed at any time in the commencement or progress of the Work by any act of neglect of the Owner, Construction Manager or the Architect, or by any employee of either, or by changes ordered in the Work, or by labor disputes, fire, unusual delay in deliveries, unavoidable casualties or any causes beyond the Contractor’s control, or by any other causes which the Architect determines may justify the delay, then the Contract Time may be extended by Change Order for such reasonable time as the Architect may determine, subject to the Owner’s approval. The Contractor shall not be entitled to additional compensation for any delays to its Work caused in whole or in part by the acts or omissions of the Owner, Construction Manager or the Architect. Any claim for loss or any delay occasioned by any separate Contractor, or Subcontractor, shall be settled between the Contractor and such other separate Contractor, or Subcontractors.

Article 9  PAYMENTS AND COMPLETION

  - SCHEDULES OF VALUES: Change this Paragraph to read as follows:

Where the Contract is based on a stipulated sum, the Contractor shall submit to the Construction Manager, at least 15 days before the first Application for Payment, a schedule of values allocating the entire Contract Sum to the various portions of the Work, and prepared in such form and supported by such data to substantiate its accuracy as the Architect may require. The Construction Manager shall forward to the Architect the Contractor’s schedule of values. This schedule, unless objected to by the Architect, Construction Manager or Owner, shall be used as a basis for reviewing the Contractor’s Application for Payment.

  - APPLICATIONS FOR PAYMENT

    - Add a new sentence to the end of this Subparagraph:

The form of Application for Payment will be AIA Document G732, Application and Certification for Payment, supported by AIA Document G703, Continuation Sheet, or a computer generated form containing similar data.

9.3.1.1	Delete this subparagraph in its entirety.

      - Add a new Clause to Subparagraph 9.3.1 as follows:

On any contract as described herein, of which the total amount is Two Hundred Fifty Thousand Dollars ($250,000.00) or greater, or on any contract with a subcontractor, regardless of amount, five percent (5%) shall be retained until the Work is at least fifty percent (50%) complete, on schedule and satisfactory in the Architect’s and/or Construction Manager’s opinion, at which time fifty percent (50%) of the retainage held to date shall be returned to the prime contractor for distribution to the appropriate subcontractors and suppliers; provided, however, that future retainage shall be withheld at the rate of two and one-half percent (2 1/2%).

      - Add a new Clause to Subparagraph 9.3.1 as follows:

The Contractor must submit each month with this Application for Payment a separate letter stating that he is requesting an extension of time or that he had no need for an extension for that period of time. No payment on a monthly application will be considered due and payable until the letter is received. Complete justification such as weather reports or other pertinent correspondence must be included for each day’s request for extension. A Contractor’s letter, or statement, will not be considered as adequate justification. The receipt of this request and data by the Owner will not be considered as Owner approval in any way.

      - Add a new Clause to Subparagraph 9.3.2 as follows:

Payment on materials stored at some location other than the building site, may be approved by the Construction Manager, Architect and the Owner after the Contractor has submitted the following items:

        - An acceptable Lease Agreement between the Contractor and the owner of the land, or building, where the materials are stored covering the specific area where the materials are located.

        - Consent of Surety, or other acceptable Bond, to cover the materials stored off-site.

        - All Perils Insurance coverage for the full value of the materials stored off-site.

        - A Bill of Sale from the Manufacturer to the Contractor for the stored materials.

        - A complete list and inventory of materials manufactured, stored and delivered to the storage site and of materials removed from the storage site and delivered to the job site.

        - A review by the Construction Manager and the Architect of the materials stored off-site prior to release of payment.

        - Guarantee no storage costs, additional delivery fees, or subsequent costs to the Owner.

9.5	DECISIONS TO WITHHOLD CERTIFICATION

9.5.4    Delete this Subparagraph in its entirety.

  - PROGRESS PAYMENTS

    - Delete this Subparagraph in its entirety.

9.6.9	Add a new Subparagraph as follows:

The amount retained by the Contractor from each payment to each Subcontractor and material supplier will not exceed the percentage retained by the Owner from the Contractor.

9.6.9.1 	Add a new Clause to Subparagraph 9.6.9 as follows:

The Contractor shall submit monthly certification on Owner’s “Affidavit Certifying Payment to All Subcontractors” form, to the Construction Manager and Architect indicating payments to subcontractors on prior payment request.

  - FAILURE OF PAYMENT

9.7.1              Change this Subparagraph to read as follows:

The Contractor and the Owner shall be subject to the remedies as prescribed in Section 31-5-25 of the Mississippi Code of 1972, Annotated.

  - SUBSTANTIAL COMPLETION

9.8.4   	Change the first sentence this Subparagraph to read as follows:

When the Work or designated portion thereof is substantially complete and affirmed by the Owner, the Architect, with assistance of the Construction Manager, will prepare a Certificate of Substantial Completion that shall establish the date of Substantial Completion, shall establish responsibilities of the Owner and Contractor for security, maintenance, heat, utilities, damage to the Work and insurance, and shall fix the time within which the Contractor shall finish all items on the list accompanying the Certificate.

  - FINAL COMPLETION AND FINAL PAYMENT

    - Change this Subparagraph to read as follows:

When, in the opinion of the Contractor, the Work is ready for final inspection and acceptance by the Owner, the Contractor shall make such notice, through the Construction Manager, to the Architect in writing.

      - Upon receipt of the Contractor’s written notice that the Work is ready for final inspection and acceptance by the Owner, the Construction Manager shall perform an inspection to confirm the completion of the work of the Contractor. The Construction Manager shall make recommendations to the Architect when the work of all contractors is ready for final inspection.  The Architect will promptly inspect the Work and compile a list of deficiencies. If, in the Architect’s judgment, the Work is not ready for inspection, another inspection will be scheduled.

      - Once the Architect has made inspection and all deficiencies listed by the Architect have been corrected and the Architect and the Construction Manager determines the Work is ready for final inspection, the Architect will call for final inspection of the Project with the Owner for the purpose of determining whether the Work is acceptable under the Contract Documents.

      - The final inspection shall be conducted in the presence of the Owner and a list of defects or discrepancies, if any, will be compiled into a punch list furnished to all parties.

      - Once corrections of all punch list items have been confirmed by the Construction Manager and Architect, the Construction Manager and the Architect will provide a letter recommending final acceptance of the Work to the Owner.

    - Change this Subparagraph to read as follows:

Retainage shall not become due until the Contractor submits to the Architect through the Construction Manager (1) final application for payment, (2) consent of surety to final payment, (3) power of attorney, (4) Contractor’s affidavit of release of liens, (5) Contractor’s affidavit of payment of debts and claims, (6) Contractor’s guarantee of work, (7) Project Record Documents and (8) certificates, warranties, guarantees, bonds or documents called for in the individual sections of the Project Manual.

  - LIQUIDATED DAMAGES

Add a new Paragraph as follows:

Time being of the essence and a matter of material consideration thereof, a reasonable estimate in advance is established to cover losses incurred by the Owner if the project is not substantially complete on the date set forth in the Contract Documents. The Contractor and his Surety will be liable for and will pay the Owner the sums stipulated in the Contract Documents as fixed and agreed as liquidated damages until the work is substantially complete unless circumstances dictate otherwise in the discretion of the Owner.

Article 10    PROTECTION OF PERSONS AND PROPERTY

  - HAZARDOUS MATERIALS

    - Delete this Subparagraph in its entirety.

    - Delete this Subparagraph in its entirety.

    - Delete this Subparagraph in its entirety.

    - Delete this Subparagraph in its entirety.

    - Delete this Subparagraph in its entirety.

Article 11  INSURANCE AND BONDS

11.2	Delete this Paragraph in its entirety.

11.3	Delete this Paragraph in its entirety.

11.4	Delete this Paragraph in its entirety.

Article 12  UNCOVERING AND CORRECTION OF WORK

No supplementary conditions.

Article 13  MISCELLANEOUS PROVISIONS

13.1	GOVERNING LAW:	Change this Title and Paragraph to read as follows:

GOVERNING LAW AND VENUE

The Contract shall be governed by the laws of the State of Mississippi. The courts of Oktibbeha County, Mississippi shall be the sole and exclusive jurisdiction and venue for any civil action related to this Agreement.

Article 14  TERMINATION OR SUSPENSION OF THE CONTRACT

No supplementary conditions.

Article 15  CLAIMS AND DISPUTES

15.1.2 Time Limits on Claims: Change this Title and Paragraph to read as follows:

COMMENCEMENT OF STATUTORY LIMITATION PERIOD

As between the Owner and Contractor:

      - Before Substantial Completion. As to acts or failures to act occurring prior to the relevant date of Substantial Completion, any applicable statute of limitations shall commence to run and any alleged cause of action shall be deemed to have accrued in any and all events not later than such date of Substantial Completion;

      - Between Substantial Completion and Final Acceptance. As to acts or failures to act occurring subsequent to the relevant date of Substantial Completion and prior to the date of Final Acceptance, any applicable statute of limitations shall commence to run and any alleged cause of action shall be deemed to have accrued in any and all events not later than the date of Final Acceptance; and

      - After the date of Final Acceptance. As to acts or failures to act occurring after the relevant date of Final Acceptance, any applicable statute of limitations shall commence to run and any alleged cause of action shall be deemed to have accrued in any and all events not later than the date of any act of failure to act by the Contractor pursuant to any Warranty provided under Section 3.5, the date of any correction of the Work or failure to correct the Work by the Contractor under Section 12.2, or the date of actual commission of any other act or failure to perform any duty or obligation by the Contractor or Owner, whichever occurs last.

15.1.7	Delete in its entirety.

15.2	INITIAL DECISION

    - Change the last sentence of this Subparagraph to read as follows:

The initial decision shall be final and binding on the parties but subject to litigation.

    - Delete this Subparagraph in its entirety.

15.2.6.1	  Delete this Clause in its entirety.

  - Delete this Paragraph in its entirety.

15.4	Delete this Paragraph in its entirety.

EXHIBIT A-1

The Construction Manager’s limits of liability shall be written for not less than the following:

- GENERAL LIABILITY:

Commercial General Liability (Including XCU)

General Aggregate...............................................$ 2,000,000.00 Aggregate

Products & Completed Operations......................$ 2,000,000.00 Aggregate

Personal & Advertising Injury..............................$ 1,000,000.00 Per Occurrence

Bodily Injury & Property Damage.......................$ 1,000,000.00 Per Occurrence

Fire Damage Liability...........................................$ 100,000.00 Per Occurrence

Medical Expense .................................................$ 10,000.00 Per Person

- AUTOMOBILE LIABILITY:  (Owned, Non-owned & Hired Vehicles)

Contractor Insurance Option Number 1:

Bodily Injury & Property Damage.................$ 1,000,000.00 Per Occurrence

(Combined Single Limit)

Contractor Insurance Option Number 2:

Bodily Injury..........................................................$ 500,000.00 Per Person

Bodily Injury........................................................$ 1,000,000.00 Per Accident

Property Damage...........................................$ 200,000.00 Per Occurrence

- EXCESS LIABILITY:

Bodily Injury & Property Damage.......................$ 2,000,000.00 Aggregate

(Combined Single Limit)

- WORKERS’ COMPENSATION: (As required by Statute)

EMPLOYERS’ LIABILITY:

Accident .........................................................$ 200,000.00 Per Occurrence

Disease ................................................................$ 1,000,000.00 Policy Limit

Disease .............................................................$ 200,000.00 Per Employee

- PROFESSIONAL LIABLITY

General Aggregate…………………………….$4,000,000.00 Aggregate

Per Occurrence…………………………………$2,000,000.00 Per Occurrence

Mississippi State University, and IHL, and each of their representatives, consultants, officers, agents, employees, directors, and trustees, regardless of whether or not identified in the Contract Documents or to the Construction Manager in writing, will be included as additional named insureds on all required insurance policies for and relating to the Project. This requirement shall not apply to Worker’s Compensation insurance.